## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Change Minds [Project location]
Enter Company Name in cell B2. | Organisation |  | Project start: | dd/mm/yyyy
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead |  | Project finish: | dd/mm/yyyy
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK |  | HUB RESOURCES | ASSIGNED TO | PROGRESS | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Initiation Phase
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Task 1 | Funding Secured |  | Project Lead |  | u
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Task 2 | Notify Change Minds Hub |  | Project Lead |  | u
| Task 3 | Notify Project Board |  | Project Lead
| Task 4 | Project Board Meeting 1 |  | Project Lead
| Task 5 | Recruitment of Project Coordinator |  | Project Lead
| Task 6 | Project Coordinator starts/induction | Project Coordinator Programme Plan | Project Lead
| Task 7 | Arrange dates for workshops and book rooms and additional staff required for delivery | This plan; mental health guidance for archive service partners | Project Coordinator
| Task 8 | Recruitment leaflets prepared using Change Minds Hub template | Leaflet template | Project Coordinator
| Task 9 | Participant Recruitment | Recruiting Participants page | Project Coordinator
| Task 10 | Initial contact between potential participants and Project Coordinator | Enrolment Form | Project Coordinator
| Task 11 | Commission Creative Facilitator/s for the Creative Phase | Creative Phase, including project roles, art form options and commissioning documents | Project Coordinator
| Task 12 | Plan Workshop 6: Participant Research Trip | Workshop 6 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 13 | Ensure travel arrangements and any support needed for attendance of workshops in place |  | Project Coordinator
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Task 14 | Prepare for evaluation | Evaluation Guide, participant information and informed consent videos | Project Coordinator
Sample phase title block | Research Phase
| Task 1 | Project Board Meeting 2 |  | Project Lead
| Task 2 | Preparation for Workshop 1 | Workshop 1 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 3 | Deliver Workshop 1: Introduction to Change Minds | Workshop 1 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 4 | Preparation for Workshop 2 | Workshop 2 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 5 | Deliver Workshop 2: Reading Archives and Choosing a Research Subject | Workshop 2 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 6 | Preparation for Workshop 3 | Workshop 3 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 7 | Deliver Workshop 3: Handling Documents | Workshop 3 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 8 | Preparation for Workshop 4 | Workshop 4 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 9 | Deliver Workshop 4: Research | Workshop 4 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 10 | Preparation for Workshop 5 | Workshop 5 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 11 | Deliver Workshop 5: Further Research | Workshop 5 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 12 | Preparation for Workshop 6 | Workshop 6 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 13 | Deliver Workshop 6: Participant Research Trip | Workshop 6 plan: Timetable, tips and downloadable resources | Project Coordinator
Sample phase title block | Creative Phase
| Task 1 | Preparation for Workshop 7 | Workshop 7 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Creative Facilitator
| Task 2 | Deliver Workshop 7: Creative Workshop | Workshop 7 plan: Timetable, tips and downloadable resources | Creative Facilitator
| Task 3 | Preparation for Workshop 8 | Workshop 8 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 4 | Deliver Workshop 8: Creative Workshop Continuation | Workshop 8 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 5 | Preparation for Workshop 9 | Workshop 9 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Creative Facilitator
| Task 6 | Deliver Workshop 9: Creative Workshop | Workshop 9 plan: Timetable, tips and downloadable resources | Creative Facilitator
| Task 7 | Preparation for Workshop 10 | Workshop 10 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 8 | Deliver Workshop 10: Creative Workshop Continuation | Workshop 10 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 9 | Preparation for Workshop 11 | Workshop 11 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 10 | Deliver Workshop 11: Final Showcase Preparation | Workshop 11 plan: Timetable, tips and downloadable resources | Project Coordinator
| Task 11 | Preparation for Workshop 12 | Workshop 12 plan: Workshop overview, Learning objectives, Materials and resources required for workshop and Preparation sections | Project Coordinator
| Task 12 | Deliver Workshop 12: Final Showcase | Workshop 12 plan: Timetable, tips and downloadable resources | Project Coordinator
Project Close Phase
| Task 1 | Ensure all evaluation materials are submitted to the project Hub | Evaluation | Project Coordinator
| Task 2 | Destruction of evaluation form hard copies |  | Project Coordinator
| Task 3 | End of project report | Template for end of project report | Project Coordinator
| Task 4 | Project Board Meeting 3 |  | Project Lead